Support file for Chapter 2

Sample Project Schedule

| No. | Task | Duration | Start | Finish | Predecessors | Resource Names |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Envisioning | 12d | Thu 11/4/99 | Fri 11/19/99 |  | Product Management |
| 2 | Create the vision/scope document | 6d | Thu 11/4/99 | Thu 11/11/99 |  |  |
| 3 | Define and write project vision statement | 2d | Thu 11/4/99 | Fri 11/5/99 |  |  |
| 4 | Define and write project scope | 2d | Mon 11/8/99 | Tue 11/9/99 | 3 |  |
| 5 | Identify business drivers and constraints | 2d | Mon 11/8/99 | Tue 11/9/99 |  |  |
| 6 | Identify critical dates | 2d | Mon 11/8/99 | Tue 11/9/99 |  |  |
| 7 | State assumptions | 2d | Mon 11/8/99 | Tue 11/9/99 |  |  |
| 8 | Gain vision/scope document approval | 2d | Wed 11/10/99 | Thu 11/11/99 | "3,4" |  |
| 9 | Plan the meeting | 1d | Wed 11/10/99 | Wed 11/10/99 |  |  |
| 10 | Obtain vision/scope document approval and signoff | 2d | Wed 11/10/99 | Thu 11/11/99 |  |  |
| 11 | Create the conceptual design | 4d | Fri 11/12/99 | Wed 11/17/99 | 8 |  |
| 12 | Develop the conceptual design | 4d | Fri 11/12/99 | Wed 11/17/99 |  |  |
| 13 | Write a high-level risk assessment | 2d | Thu 11/18/99 | Fri 11/19/99 | 11 |  |
| 14 | Assess risks and write risk assessment | 2d | Thu 11/18/99 | Fri 11/19/99 |  |  |
| 15 | Planning | 45d | Mon 11/22/99 | Fri 1/21/00 | 1 | Program Management |
| 16 | Define project structure | 5d | Mon 11/22/99 | Fri 11/26/99 |  |  |
| 17 | Assign project team roles and responsibilities | 2d | Mon 11/22/99 | Tue 11/23/99 |  |  |
| 18 | Define deployment team groups | 2d | Mon 11/22/99 | Tue 11/23/99 |  |  |
| 19 | Assess customer knowledge of Windows 2000 | 2d | Mon 11/22/99 | Tue 11/23/99 |  |  |
| 20 | Acquire reference materials and software tools | 5d | Mon 11/22/99 | Fri 11/26/99 |  |  |
| 21 | Assess and mitigate risks | 5d | Mon 11/22/99 | Fri 11/26/99 |  |  |
| 22 | Implement testing resources | 3d | Mon 11/22/99 | Wed 11/24/99 |  |  |
| 23 | Create a communications plan | 5d | Mon 11/22/99 | Fri 11/26/99 |  |  |
| 24 | Gather Information | 5d | Wed 11/24/99 | Tue 11/30/99 | 17 | Program Management |
| 25 | Identify organizational structure and business unit locations | 5d | Wed 11/24/99 | Tue 11/30/99 |  |  |
| 26 | Identify current network infrastructure | 2d | Wed 11/24/99 | Thu 11/25/99 |  | Program Management |
| 27 | Physical network topology | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 28 | Protocol address management | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 29 | Host name resolution services | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 30 | Microsoft Windows 2000 Server domain structure | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 31 | Remote access | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 32 | Network operations/performance management | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 33 | Identify current infrastructure | 3d | Wed 11/24/99 | Fri 11/26/99 |  |  |
| 34 | Naming conventions | 3d | Wed 11/24/99 | Fri 11/26/99 |  |  |
| 35 | External connectivity | 3d | Wed 11/24/99 | Fri 11/26/99 |  |  |
| 36 | Backbone | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 37 | Technical support | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 38 | Operations | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 39 | Training | 2d | Wed 11/24/99 | Thu 11/25/99 |  |  |
| 40 | Identify current desktop environment | 3d | Wed 11/24/99 | Fri 11/26/99 |  |  |
| 41 | Desktop user profiles | 3d | Wed 11/24/99 | Fri 11/26/99 |  |  |
| 42 | Identify functional requirements | 4d | Wed 11/24/99 | Mon 11/29/99 |  |  |
| 43 | Administrative functionality | 4d | Wed 11/24/99 | Mon 11/29/99 |  |  |
| 44 | User functionality | 4d | Wed 11/24/99 | Mon 11/29/99 |  |  |
| 45 | Define desired end state | 3d | Wed 11/24/99 | Fri 11/26/99 |  |  |
| 46 | Create the end state diagram | 3d | Wed 11/24/99 | Fri 11/26/99 |  |  |
| 47 | Describe messaging system connectivity | 3d | Wed 11/24/99 | Fri 11/26/99 |  |  |
| 48 | Conduct a gap analysis | 7d | Wed 12/1/99 | Thu 12/9/99 | 24 |  |
| 49 | Assess infrastructure readiness | 7d | Wed 12/1/99 | Thu 12/9/99 |  |  |
| 50 | Coexistence infrastructure | 7d | Wed 12/1/99 | Thu 12/9/99 |  |  |
| 51 | Determine gaps in user functionality | 7d | Wed 12/1/99 | Thu 12/9/99 |  |  |
| 52 | Determine high priority new functionality | 7d | Wed 12/1/99 | Thu 12/9/99 |  |  |
| 53 | Define the service offering | 10d | Fri 12/10/99 | Thu 12/23/99 | 48 |  |
| 54 | Specify functionality to be delivered | 10d | Fri 12/10/99 | Thu 12/23/99 |  |  |
| 55 | Specify performance criteria | 10d | Fri 12/10/99 | Thu 12/23/99 |  |  |
| 56 | Specify operational constraints | 10d | Fri 12/10/99 | Thu 12/23/99 |  |  |
| 57 | Sign off on service offering | 10d | Fri 12/10/99 | Thu 12/23/99 |  |  |
| 58 | Build the master project plan | 21d | Fri 12/24/99 | Fri 1/21/00 | 53 |  |
| 59 | Identify the plan owner | 21d | Fri 12/24/99 | Fri 1/21/00 |  |  |
| 60 | Build the master project plan | 21d | Fri 12/24/99 | Fri 1/21/00 |  |  |
| 61 | Update the master project plan | 21d | Fri 12/24/99 | Fri 1/21/00 |  |  |
| 62 | Developing | 619d | Wed 10/15/97 | Mon 2/28/00 | 58 | Development |
| 63 | Create the logical design | 619d | Wed 10/15/97 | Mon 2/28/00 |  |  |
| 64 | Describe network infrastructure | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 65 | Physical network infrastructure | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 66 | Windows 2000 Server domain model | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 67 | Protocol address management | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 68 | Host name resolution | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 69 | Remote access | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 70 | Naming standards | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 71 | Security | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 72 | Describe Microsoft Exchange backbone | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 73 | Microsoft Exchange site topology | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 74 | Directory replication | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 75 | Server placement | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 76 | Server sizing | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 77 | External connectivity | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 78 | Naming standards | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 79 | Public folders | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 80 | Forms management | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 81 | Security encryption key management | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 82 | Administrative model | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 83 | Web connectivity | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 84 | POP3 connectivity | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 85 | LDAP connectivity | 25d | Mon 1/24/00 | Fri 2/25/00 |  |  |
| 86 | Define coexistence and migration infrastructure | 26d | Mon 1/24/00 | Mon 2/28/00 |  |  |
| 87 | Directory synchronization | 26d | Mon 1/24/00 | Mon 2/28/00 |  |  |
| 88 | Messaging coexistence | 26d | Mon 1/24/00 | Mon 2/28/00 |  |  |
| 89 | Mail enabled applications | 26d | Mon 1/24/00 | Mon 2/28/00 |  |  |
| 90 | Deployment | 26d | Mon 1/24/00 | Mon 2/28/00 |  |  |
| 91 | Server installation and configuration | 26d | Mon 1/24/00 | Mon 2/28/00 |  |  |
| 92 | Client installation and configuration | 26d | Mon 1/24/00 | Mon 2/28/00 |  |  |
| 93 | Site deployment process | 26d | Mon 1/24/00 | Mon 2/28/00 |  |  |
| 94 | Training | 26d | Mon 1/24/00 | Mon 2/28/00 |  |  |
| 95 | Operations and systems management | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 96 | Technical support | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 97 | Operations | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 98 | Validate and approve logical design | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 99 | Peer review | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 100 | Validate logical design | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 101 | Sign off on logical design | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 102 | Compile list of deliverables for build phase | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 103 | Build the design | 594d | Wed 10/15/97 | Mon 1/24/00 |  |  |
| 104 | General considerations | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 105 | Test-as-you-go approach | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 106 | Track progress | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 107 | Perform multiple revisions | 10d | Wed 10/15/97 | Tue 10/28/97 |  |  |
| 108 | Implement network infrastructure | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 109 | Physical network infrastructure | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 110 | Windows 2000 Server domain model | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 111 | Protocol management services | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 112 | Host name resolution services | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 113 | Remote access services | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 114 | Security | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 115 | Describe Microsoft Exchange backbone | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 116 | Exchange site topology | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 117 | Directory replication | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 118 | Server placement | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 119 | Server sizing | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 120 | External connectivity | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 121 | Naming standards | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 122 | Public folders | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 123 | Forms management | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 124 | Security encryption key | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 125 | Administrative model | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 126 | Internet Web connectivity | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 127 | Non-map connectivity | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 128 | Implement coexistence and migration infrastructure | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 129 | Directory synchronization | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 130 | Messaging coexistence | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 131 | Develop deployment procedures | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 132 | Server deployment | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 133 | Client deployment | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 134 | Site deployment process and checklist | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 135 | Migration scenarios | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 136 | Training | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 137 | Develop operations and systems processes | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 138 | Technical support | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 139 | Operations | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 140 | Perform a load simulation | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 141 | Microsoft Exchange backbone | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 142 | External connectivity | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 143 | Performance monitoring | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 144 | Operations | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 145 | Conduct the pilot and controlled introduction | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 146 | Define scope and objectives for pilot and controlled introduction | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 147 | Select pilot and controlled introduction sites | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 148 | "Design, plan, and implement the pilot and controlled introduction" | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 149 | Evaluate the pilot and controlled introduction | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 150 | Complete the pilot and controlled introduction and document the results | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 151 | Move from controlled introduction to enterprise-wide deployment | 1d | Mon 1/24/00 | Mon 1/24/00 |  |  |
| 152 | Deployment | 30d | Tue 2/29/00 | Mon 4/10/00 | 62 |  |
| 153 | Deploy the system | 14d | Tue 2/29/00 | Fri 3/17/00 |  |  |
| 154 | Location deployment process | 14d | Tue 2/29/00 | Fri 3/17/00 |  |  |
| 155 | Site surveys | 14d | Tue 2/29/00 | Fri 3/17/00 |  |  |
| 156 | Site template project plan | 14d | Tue 2/29/00 | Fri 3/17/00 |  |  |
| 157 | Appropriate implementation scripts | 14d | Tue 2/29/00 | Fri 3/17/00 |  |  |
| 158 | Training materials | 14d | Tue 2/29/00 | Fri 3/17/00 |  |  |
| 159 | Certification document | 14d | Tue 2/29/00 | Fri 3/17/00 |  |  |
| 160 | Installation evaluation | 14d | Tue 2/29/00 | Fri 3/17/00 |  |  |
| 161 | Monitor user satisfaction | 30d | Tue 2/29/00 | Mon 4/10/00 |  |  |
| 162 | Gather requirements for future versions | 30d | Tue 2/29/00 | Mon 4/10/00 |  |  |
| 163 | Implement operational systems | 30d | Tue 2/29/00 | Mon 4/10/00 |  |  |