Migration Project Risk Assessment

The first section of this document provides an overview of risk management, along with forms for assessing risks involved in a Web server migration project. The second section provides a risk assessment checklist for the some of the most common risk factors. The third section explains the categories used in the actual risk assessment forms found in the fourth section.

For examples of risk factors to consider for your project, see the file, RiskFactorsChartTemplate.xls, available at the Microsoft Solutions Framework Web site:

http://www.microsoft.com/MSF/

# Planning Risk Management

Every successful project needs a risk management plan based on the initial risk assessment for the project.  The project team performs the initial risk assessment during the envisioning phase. Microsoft Solutions Framework (MSF) guidelines recommend using risk factor tables to perform the initial risk assessment. Risk factors tables are built from organizational knowledge based on lessons learned from previous projects and on general industry experience.

Once the team completes the initial risk assessment, it can proceed with the ongoing process of risk management. This process will include:

- Determining which risks should be dealt with first. This is determined by the risk analysis process.

- Planning how to deal with risks once they are defined. This process depends on the risks and will be the basis of the initial risk action plan.

- How often to review and update risks. Remember that effective risk management is an ongoing process and a forefront task. Therefore, risks should be reviewed on an ongoing basis at status meetings and be referred to in status reports.

Note   Risks change over time, so it is important to keep track of their status. The best way is to use some automated method such as a word processing document, a spreadsheet, or ideally, a database like the issues (bug) database.

Do not list problems as risks. If something is definitely going to happen or has happened, it is a problem and should be treated as such.

# Task-Based Risk Assessment Checklist

## Schedule Risks

- Tasks that are exceptionally complicated.

- Tasks that require more than two weeks to complete.

- Tasks on the critical path.

- Tasks that have several predecessors.

- Tasks that have minimal slack.

- Tasks that are optimistically estimated.

- Tasks reliant on external groups.

- Start-to-Start and Finish-to-Finish dependencies.

- Dependencies with lags.

- Major milestones.

- Unforeseen issues (for example, reorganizations and office moves).

- Unstated assumptions.

## Resource Risks

- Tasks with one key individual assigned.

- Tasks using scarce resources.

- Tasks that are mismatched with the people assigned.

- Tasks that require large numbers of resources.

- Availability of tools and/or techniques.

- Tasks that rely on third-party vendors for their completion.

- Tasks that rely on resources within another group for their completion.

## Scope Risks

- Uncertainty of new technology.

- Dynamics of customer requirements.

- Tasks with significant business impact.

- Extremely aggressive performance requirements.

## Preventative Tasks to Mitigate Risk

- Add resources to tasks for cross-training.

- Establish independent parallel efforts.

- Schedule high risk tasks earlier in the development cycle.

- Reduce project scope.

- Add review tasks.

- Shift more experienced people to tasks.

- Design in redundancy.

- Change the approach to eliminate high-risk tasks.

- Add prototyping tasks to prove concepts.

# Explanation of Assessment Categories

## Risk

In this field, give each risk a unique and descriptive name that makes them easy to identify.

## Description

This field can contain two descriptions: 1) a brief description of the risk and how it affects the process and 2) a more detailed description that lets the project team and the customer better understand how the risk affects the project.

It is important to provide a detailed description so that other team members can contribute ideas about how to mitigate those risks. Here are examples of brief and detailed descriptions:

- Brief description   “An important customer uses XYZ application. The compatibility of the XYZ application with Windows 2000 Server is unknown.”

- Detailed description   “The Windows 2000 Server Product Group at Microsoft has not yet tested the XYZ application. The application was tested on site by our project team and failed acceptance criteria (6/25). The software manufacturer has committed to making code changes and expects to provide us updated software in about five days (7/1).”

The dates in parentheses indicate when the action took place. This information is needed to establish an audit trail for the mitigation of risks.

## Level of Impact

In this field, assign a level of impact to the risk—low, medium, or high.

- Low-impact risks are not critical. Should they occur, however, they might delay (but not interrupt) the deployment process. You should mitigate low-impact risks within a few weeks following their identification.

- Medium-impact risks can be critical. Should they occur, they might interrupt part of the process. Mitigate medium-impact risks within several days after they are identified.

- High-impact risks are critical because they can jeopardize the entire project. Should they occur, these risks will interrupt part or all of the process. Mitigate high-impact risks immediately. The Web server migration process should stop either until these risks are resolved or until the project team agrees to structure the plan around them.

## Exposure

In this field, assign a percentage that specifies the likelihood the risk will occur. When used with risk impact levels, a risk probability can help you determine the risk resolution priority level. For example, a high-probability, high-impact risk should be dealt with immediately. A low-probability, low-impact risk will likely have very little impact and can be deferred.

## Date

In this field, specify the date the risk was originally identified. This date does not change throughout the deployment project.

## Owner

Specify the risk owner in this field. The owner is the person or group most closely affected by the risk or responsible for accomplishing the tasks related to the risk. In the example provided in Description, the owner will most likely be the group in charge of application certification and testing.

## Mitigation Plan

In this field, provide a detailed description of how the risk will be eliminated or reduced. Mitigation presents alternatives for resolution that can involve a change in the project plan and procedures. For example: “This XYZ application is used by only 2 percent of the targeted user community. If code changes provided by the manufacturer do not resolve current problems, we will take those 2 percent of users out of the project scope. Develop an alternative plan that takes this change into account and notify the XYZ team leader (7/1).”

Note the date in parentheses. It is essential to include dates in the description because as risk descriptions change, the mitigation options can also change.

# Risk Assessment Forms

## High-Level Risks

This section of the risk assessment form outlines the upcoming technologies and organizational issues that might affect progress of the project. This checklist can be used to ensure that all bases are covered for project success.

| Risk | Description | Level of Impact | Proba-bility | Date | Owner | Mitigation Plan |
| --- | --- | --- | --- | --- | --- | --- |
| Budget | Not enough management commitment to the project to get the necessary budget. |  |  |  |  |  |
| Human resources | Not enough people available. People with the appropriate technical expertise are not available. |  |  |  |  |  |
| Conflicting projects | Other projects that compete for the same resources will be underway at the same time as our project. |  |  |  |  |  |
| Differing visions | Members of various sponsoring organizations have differing visions of the project outcomes and methods. |  |  |  |  |  |
| Deadlines | Project deadlines are not realistic. |  |  |  |  |  |

## Personnel/Project Role Definition Risks

Personnel assessment is necessary to provide the proper level of staffing and to maintain project focus and coordination. Project efficiency is maximized when key members have clearly established project roles and responsibilities.

| Risk | Description | Level of Impact | Proba-bility | Date | Owner | Mitigation Plan |
| --- | --- | --- | --- | --- | --- | --- |

## Project Plan Risks

Mitigating risks to the project plan is key to maintaining a project timeline and defining the pilot completion stage.

| Risk | Description | Level of Impact | Proba-bility | Date | Owner | Mitigation Plan |
| --- | --- | --- | --- | --- | --- | --- |

### Operations and Support Risks

Operations and technical support is a critical part of the pilot process and mitigating risks in this area can minimize impact to the project schedule.

| Risk | Description | Level of Impact | Proba-bility | Date | Owner | Mitigation Plan |
| --- | --- | --- | --- | --- | --- | --- |

### Project Communication Risks

Project efficiency is maximized when there is a formal process for exchanging key project information.

| Risk | Description | Level of Impact | Proba-bility | Date | Owner | Mitigation Plan |
| --- | --- | --- | --- | --- | --- | --- |

Ó 1999 Microsoft Corporation. All rights reserved.

The information contained in this document represents the current view of Microsoft Corporation on the issues discussed as of the date of publication. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information presented after the date of publication.

This document is for informational purposes only. MICROSOFT MAKES NO WARRANTIES, EXPRESS OR IMPLIED, IN THIS DOCUMENT.

Microsoft is either a registered trademark or a trademark of Microsoft in the United States and/or other countries.